## Sheet1
Team Number: 9
TEAM SCHEDULE
On this schedule, you will plan the successful completion of all Tasks' deliverables, using the resources of the whole team.
Each team must maintain one version of this schedule. You are not to modify the structure of this schedule in any way.
The manager is responsible for keeping this schedule up to date and for making sure that everyone on the team
has access to the latest version of it. You must submit the most current version of this schedule with each deliverable.
Below I have listed jobs required to complete the four Tasks. You must completely fill in the whole schedule with
names, dates and times before submitting Task 1. If you want to, you may add rows with additional jobs that your team
must complete. The only columns to be left blank for now is the "Date and Time Completed" and "Person Completing".
You will fill those columns in as each job is completed. Do not start the project until every team member understands
what every one of these jobs entail! Ask any questions during a meeting or in the public Discussion.
|  | Date and | Person |  | Date and Time | Person
ID # | Job Name | time due | Responsible | Predecessors | Completed | Completing
Jobs required for Task 1
10 | Set up Github account | 5/28/2017 6:00pm | Christian
11 | Draft of schedule to team | 5/28/2017 6:00pm | Xinyu
12 | Feedback on schedule | 5/30/2017 6:00pm | Christian, Erin | 10
13 | Final Schedule to Elaine | 6/1/2017 9:00am | Erin | 11
14 | Draft of contract to team | 5/28/2017 6:00pm | Erin
15 | Feedback on contract | 5/30/2017 6:00pm | Christian, Xinyu | 13
16 | Final contract to Elaine | 6/1/2017 9:00am | Erin | 14
Jobs required for Task 2
20 | First draft of class skeleton to team | 6/4/2017 6:00pm | Christian | 12,15
21 | First draft of list of prewritten classes to team | 6/4/2017 6:00pm | Xinyu | 12,15
22 | First draft of UI design to team | 6/4/2017 6:00pm | Erin | 12,15
23 | Feedback on class skeleton to author | 6/6/2017 6:00pm | Erin, Xinyu | 20
24 | Feedback on list of prewritten classes to author | 6/6/2017 6:00pm | Christian, Erin | 21
25 | Feedback on UI design to author | 6/6/2017 6:00pm | Christian, Xinyu | 22
26 | Second Draft of all documents to Elaine | 6/8/2017 9:00am | Erin | 23,24,25
27 | Feedback on all three documents from Elaine | 6/9/2017 9:00am | Elaine | 26
28 | Third draft of class skeleton to team | 6/11/2017 9:00am | Christian | 27
29 | Third draft of list of prewritten classes to team | 6/11/2017 9:00am | Xinyu | 27
30 | Third draft of UI design to team | 6/11/2017 9:00am | Erin | 27
31 | Feedback on class skeleton to author | 6/12/2017 6:00pm | Erin, Xinyu | 28
32 | Feedback on list of prewritten classes to author | 6/12/2017 6:00pm | Christian, Erin | 29
33 | Feedback on UI design to author | 6/12/2017 6:00pm | Christian, Xinyu | 30
34 | Fourth draft of all documents to Elaine | 6/13/2017 9:00am | Erin | 31,32,33
35 | Feedback on all documents from Elaine | 6/14/2017 9:00am | Elaine | 34
Jobs required for Task 3
50 | First draft of Use Case 1 implementation to team | 6/16/2017 6:00pm | Christian | 35
51 | Feedback and bug reports on draft of Use Case 1 implementation to author | 6/18/2017 6:00pm | Erin, Xinyu | 50
52 | Second draft of Use Case 1 implementation to Elaine | 6/20/2017 9:00am | Erin | 51
53 | Feedback on Use Case 1 code from Elaine | 6/21/2017 9:00am | Elaine | 52
Jobs required for Task 4
54 | First draft of Use Case 2 implementation to team | 6/23/2017 9:00am | Erin | 53
55 | First draft of Use Case 3 implementation to team | 6/23/2017 9:00am | Christian | 53
56 | First draft of Use Cases 4,5 implementation to team | 6/23/2017 9:00am | Xinyu | 53
57 | Feedback on Use Case 2 implementation to author | 6/25/2017 9:00am | Christian, Xinyu | 54
58 | Feedback on Use Case 3 implementation to author | 6/25/2017 9:00am | Erin, Xinyu | 55
59 | Feedback on Use Case 4,5 implementation to author | 6/25/2017 9:00am | Christian, Erin | 56
60 | Final code for Use Case 2 implementation to team | 6/26/2017 6:00pm | Erin | 57
61 | Final code for Use Case 3 implementation to team | 6/26/2017 6:00pm | Christian | 58
62 | Final code for Use Cases 4,5 implementation to team | 6/26/2017 6:00pm | Xinyu | 59
63 | Integration testing complete and source code submitted to Elaine | 6/27/2017 9:00am | Erin | 60,61,62
64 | All other documents updated and submitted to Elaine | 6/27/2017 9:00am | Erin | 63
Before you submit this schedule as part of your Task 1 deliverable, fill in names, dates and times for all jobs in ALL Tasks.
The only columns to be left blank for now is the "Date and Time Completed" and "Person Completing" for Tasks 2, 3, and 4.
When you give feedback on a deliverable, you must give at least two suggestions for improvement. If you cannot show
at least two suggestions for improvement that you gave the author of a deliverable, you will not get credit for that Task.